## 1. Instructions
Failure Mode & Effects Analysis: FMEA-Lite Templates -- Instructions
1. For the most important activities (steps) or deliverables in a process: Identify potential problems (failure modes)
2. Assign SEV, OCC, and DET scores to each
3. Calculate the Risk Priority Number:
RPN = SEV x OCC x DET
For the problem(s) with the highest RPN, do the following
4. Identify causes. Develop preventions or mitigations for the causes and/ or the problems.
5. Estimate the results: assign SEV, OCC, DET scores to the process after preventions/ mitigations are implemented.
Calculate the estimated "To Be" RPN
6. If the To-Be RPN is estimated to be a satisfactory improvement, implement the preventions or mitigations.
7. Calculate the post-improvement RPN.
8. Compare this with the RPNs of all the other problems. And repeat, starting with Step 4, for the problem which now has the highest RPN.
You may decide on a company policy that all risk items (Failure Modes)s with scores above a certain threshold must be addressed.
As shown in sheet #4, full Failure Mode Effects Analysis is often done with 10 gradations of importance for each of SEV, OCC and DET.
For our FMEA-Lite version on sheet #3, we have 5 gradations of SEV, and 3 each for OCC and DET
Send feedback to Andy Jawlik: andy@jawlikassoc.com

## 2. FMEA-Lite Example
2. FMEA-lite Example
Threshold for action: 3 x 3 x 2 = 18
| As - Is |  |  |  | Est. To-Be, 1st round
Problem | SEV | OCC | DET | RPN | SEV | OCC | DET | RPN
Main Speaker doesn't show up | 6 | 2 | 3 | 36 | 4 | 2 | 2 | 16
Projector doesn't work | 4 | 3 | 1 | 12 | 4 | 3 | 1 | 12
Handouts don't arrive on time | 2 | 2 | 3 | 12 | 2 | 2 | 3 | 12
Sound System doesn't work | 3 | 2 | 3 | 18 | 3 | 2 | 3 | 18
Ambient Noise is distracting | 2 | 2 | 2 | 8 | 2 | 2 | 2 | 8
Meals taste terrible | 4 | 1 | 3 | 12 | 4 | 1 | 3 | 12
As-Is: two problems meet the threshhold for action, so we should address both of these -- at least.
To-Be: Start with the problem with highest-Risk Priority Number and design mitigations and preventions. Estimate their effect on SEV, OCC, and DET
Send feedback to Andy Jawlik: andy@jawlikassoc.com

## 3. FMEA-Lite Template
3. FMEA-Lite Template
For each problem you enter in col. b, select a SEV, OCC & RPN scores. Click on the cells in columns c, d, and, and a drop-down of acceptable scores is shown. RPN will be calculated. Select the highest priority items for action and design preventions and/ or mitigations. Estimate how these would effect the the SEV, OCC, and DET scores in the To-Be state. If they project to be sufficiently improved, implement the improvements.
|  | As-Is |  |  |  | Estimated To-Be
ID# | Problem/ Failure Mode | SEV | OCC | DET | RPN | SEV | OCC | DET |  | RPN
1 |  |  |  |  | 0 |  |  |  |  | 0 | Note that this spreadsheet is password-protected so that the formulas and drop-downs don't get overridden. If you have a need to change anything other than the input fields, you can unprotect the spreadsheet by using the password, "password".
2 |  |  |  |  | 0 |  |  |  |  | 0
3 |  |  |  |  | 0 |  |  |  |  | 0
4 |  |  |  |  | 0 |  |  |  |  | 0
5 |  |  |  |  | 0 |  |  |  |  | 0
6 |  |  |  |  | 0 |  |  |  |  | 0
7 |  |  |  |  | 0 |  |  |  |  | 0
8 |  |  |  |  | 0 |  |  |  |  | 0
9 |  |  |  |  | 0 |  |  |  |  | 0
Value Choices for the drop-downs above
| Severity | SEV |  | Occurs | OCC | Detect &Fix Before Customer Notices |  |  | DET
| Disaster | 6 |  | Frequently | 4 | Unlikely |  |  | 3
| Big Problem | 4 |  | Occasionally | 3 | 50 - 50 |  |  | 2
| Problem | 3 |  | Rarely | 2 | Likely |  |  | 1
| Small Problem | 2
| Annoyance | 1

## 4. FMEA-heavy Scores
Here's an illustration of a scoring systems with more levels of gradation. The values for each score can vary, depending on the industry and the problem.
For example, a high-quality manufacturing company would have much more stringent requirements in OCC and DET
You can find many examples on the web by just searching for "FMEA" or ""FMEA-Lite"